## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (ETL Pipeline Overview) | MUST HAVE | No Dependency | K G Soumya | 3 - Completed
S1 | S1 | US-002 | Workflow Creation and Project Goal Document | MUST HAVE | No Dependency | K G Soumya | 3 - Completed
S2 | S2 | US-003 | Dataset Creation and Cleaning (Student Data) | MUST HAVE | No Dependency | K G Soumya | 3 - Completed
S2 | S2 | US-004 | ETL Implementation (Extract, Transform, Load) | MUST HAVE | No Dependency | K G Soumya | 3 - Completed
S3 | S3 | US-005 | Kafka Setup using Docker | MUST HAVE | Docker | K G Soumya | 3 - Completed
S3 | S3 | US-006 | Kafka Producer and Consumer Implementation | MUST HAVE | Kafka | K G Soumya | 3 - Completed
S4 | S4 | US-007 | Spark Data Processing Integration | MUST HAVE | Kafka | K G Soumya | 3 - Completed
S4 | S4 | US-008 | Data Transformation and Analytics Logic | MUST HAVE | Spark | K G Soumya | 3 - Completed
S5 | S5 | US-009 | Airflow Setup and DAG Creation | MUST HAVE | Airflow | K G Soumya | 2 - In Progress
S5 | S5 | US-010 | Workflow Automation using Airflow | MUST HAVE | Airflow | K G Soumya | 2 - In Progress
S6 | S6 | US-011 | Flask API Development | MUST HAVE | Python | K G Soumya | 3 - Completed
S6 | S6 | US-012 | Frontend Dashboard (Multi-page UI) | MUST HAVE | HTML/CSS/JS | K G Soumya | 3 - Completed
S7 | S7 | US-013 | Analytics Page (Charts & Insights) | SHOULD HAVE | Chart.js | K G Soumya | 3 - Completed
S7 | S7 | US-014 | Search and Filter Functionality | SHOULD HAVE | Frontend | K G Soumya | 3 - Completed
S8 | S8 | US-015 | Email Alert Integration (SMTP) | SHOULD HAVE | SMTP | K G Soumya | 2 - In Progress
S8 | S8 | US-016 | Testing and Debugging | MUST HAVE | All Modules | K G Soumya | 2 - In Progress
S8 | S8 | US-017 | Final Deployment and Presentation | MUST HAVE | Complete Project | K G Soumya | 2 - In Progres
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 66 | 26 | 17 | 15 | 7 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
S-001 | 1 | Introduction to project (ETL Overview) | 2026-03-01 | 2026-03-02 | K G Soumya | K G Soumya | 3 - Completed | 2 | Day 1: 1; Day 2: 1; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0
US-002 | 2 | Workflow Creation & Goal Document | 2026-03-03 | 2026-03-04 | K G Soumya | K G Soumya | 3 - Completed | 2 | Day 1: 1; Day 2: 1; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0
US-003 | 3 | Dataset Creation & Cleaning | 2026-03-05 | 2026-03-06 | K G Soumya | K G Soumya | 3 - Completed | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0
US-004 | 4 | ETL Implementation | 2026-03-07 | 2026-03-09 | K G Soumya | K G Soumya | 3 - Completed | 4 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 0; Day 6: 0
US-005 | 5 | Kafka Setup (Docker) | 2026-03-10 | 2026-03-12 | K G Soumya | K G Soumya | 3 - Completed | 5 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 0
US-006 | 6 | Kafka Producer & Consumer | 2026-03-13 | 2026-03-15 | K G Soumya | K G Soumya | 3 - Completed | 5 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1
US-007 | 7 | Spark Processing Integration | 2026-03-16 | 2026-03-18 | K G Soumya | K G Soumya | 3 - Completed | 6 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1
US-008 | 8 | Data Transformation Logic | 2026-03-19 | 2026-03-20 | K G Soumya | K G Soumya | 3 - Completed | 5 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 0; Day 6: 0
US-009 | 9 | Airflow Setup & DAG | 2026-03-21 | 2026-03-23 | K G Soumya | K G Soumya | 2 - In Progress | 6 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1
US-010 | 10 | Workflow Automation | 2026-03-24 | 2026-03-25 | K G Soumya | K G Soumya | 2 - In Progress | 4 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0
US-011 | 11 | Flask API Development | 2026-03-26 | 2026-03-27 | K G Soumya | K G Soumya | 3 - Completed | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0
US-012 | 12 | Frontend Dashboard UI | 2026-03-28 | 2026-03-30 | K G Soumya | K G Soumya | 3 - Completed | 5 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1
US-013 | 13 | Analytics Page (Charts) | 2026-03-31 | 2026-04-01 | K G Soumya | K G Soumya | 3 - Completed | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0
US-014 | 14 | Search & Filter Feature | 2026-04-02 | 2026-04-03 | K G Soumya | K G Soumya | 3 - Completed | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0
US-015 | 15 | Email Alert Integration | 2026-04-04 | 2026-04-05 | K G Soumya | K G Soumya | 2 - In Progress | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0
US-016 | 16 | Testing & Debugging | 2026-04-05 | 2026-04-06 | K G Soumya | K G Soumya | 2 - In Progress | 4 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0
US-017 | 17 | Final Deployment & Presentation | 2026-04-07 | 2026-04-07 | K G Soumya | K G Soumya | 2 - In Progress | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on ETL pipeline flow and tools | Conducted research and referred documentation to understand ETL architecture
Sprint 1 | Day 4 | Difficulty in defining project goals and workflow | Created workflow diagram and finalized project structure
Sprint 2 | Day 6 | Confusion in Agile template and backlog creation | Referred sample templates and structured backlog properly
Sprint 2 | Day 7 | Difficulty in preparing dataset with correct attributes | Cleaned dataset and ensured proper column formatting
Sprint 2 | Day 9 | Confusion in prioritizing tasks in ETL pipeline | Prioritized tasks based on pipeline flow (Extract → Transform → Load)
Sprint 3 | Day 12 | Errors while setting up Kafka using Docker | Restarted Docker and manually pulled images to fix issues
Sprint 3 | Day 14 | Kafka producer/consumer connection issues | Verified ports and corrected Kafka configuration
Sprint 4 | Day 16 | Spark integration errors and data processing issues | Debugged code and optimized Spark transformations
Sprint 5 | Day 20 | Airflow DAG not triggering properly | Fixed DAG path and verified Airflow setup
Sprint 6 | Day 23 | Frontend not fetching data from API | Ensured Flask API is running and corrected endpoint URL
Sprint 7 | Day 25 | Difficulty in designing multi-page frontend | Improved UI structure and separated pages (Dashboard, Students, Analytics)
Sprint 8 | Day 27 | Issues in email alert integration (SMTP errors) | Used App Password and corrected SMTP configuration
Sprint 8 | Day 28 | Final integration issues across modules | Tested full pipeline and fixed minor bugs

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-03-01 | 2026-03-04 | K G Soumya | Understanding ETL concepts and project structure | Avoid unclear planning | Continue learning fundamentals | Created project workflow and documentation
2 | Sprint 2 | 2026-03-05 | 2026-03-09 | K G Soumya | Dataset creation and ETL implementation | Stop inconsistent data formatting | Continue structured data processing | Cleaned dataset and implemented ETL logic
3 | Sprint 3 | 2026-03-10 | 2026-03-15 | K G Soumya | Kafka setup and streaming implementation | Stop random debugging without logs | Continue step-by-step debugging | Successfully integrated Kafka producer & consumer
4 | Sprint 4 | 2026-03-16 | 2026-03-20 | K G Soumya | Spark processing and transformations | Avoid inefficient code practices | Continue optimizing logic | Improved Spark transformations
5 | Sprint 5 | 2026-03-21 | 2026-03-25 | K G Soumya | Airflow DAG creation and scheduling | Stop incorrect file placements | Continue workflow automation | Fixed DAG issues and scheduling
6 | Sprint 6 | 2026-03-26 | 2026-03-30 | K G Soumya | Flask API and frontend development | Stop hardcoding values | Continue modular coding | Built API and connected frontend
7 | Sprint 7 | 2026-03-31 | 2026-04-05 | K G Soumya | Testing and UI improvements | Avoid ignoring minor bugs | Continue debugging and testing | Fixed errors and improved UI
8 | Sprint 8 | 2026-04-06 | 2026-04-07 | K G Soumya | Final integration and presentation | Stop last-minute changes | Continue reviewing project | Completed project presentation successfully